## Sheet1
Task | Progress | ASSIGNED TO | Last Update
Notes:
Part 1: Project Specification |  |  |  | Save Requirements Doc for Both .doc and .pdf
Create Idea for Project | Yes | Ryan | 2017-02-22 | Ask Naz about what she wants for the UI mock-up
Check if idea is feasible based on requirements
Set Up GitLab Server | Yes | Kenneth | 2017-02-22
Expand on possible features and constraints | In-progress | Multiple | 2017-02-22
Part 2: Mock-up
Design a prototype interface design
Find an arbritrary math question and images for mock-up
Create UI Mockup on eclipse (API 16)
Part 3: Requirement Document
Domain
Problem and sub-problems
Purpose and audience
Storyline
Required Functionality
Desired Functionality
Save in BOTH .doc and .pdf
Part 4: Requirement Document Review and Validation
Grammar Mistakes
Ambiguity
Completeness
Consistency
Formality
Organization
Clearness
Check over (6) and (7) of the scum outline
Submit Assignment
Part 5: Self-reflection
Create a read-me file documenting all of the things you did. |  | EVERYONE
Install Android Studio and get familiarized with GitLab |  | EVERYONE